## Milestone 3 Work Plan
BAMA 520 — Group 3 ¦ Milestone 3 Work Plan
Updated based on professor feedback — 48-hour sprint to Wednesday presentation
Task | Details | Owner | Output | Status
Team alignment call | Common key, repeat buyer definition, monetary = price only agreed. | All 5 | Shared definitions doc | Done
Data loading & joins | All 8 CSVs cleaned, joined. Master table: 96,470 rows × 25 cols. | Hanna + Manvi | orders_full.rds | Done
RFM feature engineering | 93,349 customers, 18 features, 3% repeat rate confirmed. | Hanna + Manvi | rfm_table.rds | Done
CLV estimation | CLV = P(repeat) × avg_order_value × frequency. Repeat buyers BRL 260 vs BRL 4.14 one-time — 60x gap. | Selina | CLV scores table | Done
Dollar impact calculation | 3%→5%: BRL 542,532. 3%→6%: BRL 813,876. No incremental acquisition cost. | Selina | Revenue impact table | Done
Delivery delay analysis | Effect is gradual — no single sharp threshold. Earlier first deliveries associated with higher repeat rates. | Shrikar+Augus | Delay threshold finding | Done
Experience signal analysis | Vouchers (3.81x OR) and installments outperform delivery timing and review scores as predictors. | Augus+Shrikar | Experience driver summary | Done
Binary classifier | Logistic regression, AUC 0.743. Leakage-free (recency & frequency excluded). 1,202 customers with P(repeat) ≥ 10%. | Augus+Shrikar | P(repeat) score per customer | Done
Feature importance ranking | Voucher usage #1 (3.81x), installments #2, monetary #3, freight #4, delivery delay #5. Review score not significant. | Manvi+Hanna | Feature importance ranking | Done
Milestone 2 submission | Submitted via Canvas. Prof feedback received. | All 5 | Submitted deliverable | Done
Priority 1 — Targeting P&L (most important)
Build targeting P&L | Use 1,202 customers with P(repeat) >= 10% from scoring table. Assume BRL 10 voucher + BRL 5 delivery = BRL 15 per customer. Total cost = 1,202 x BRL 15 = BRL 18,030. Expected conversions = 1,202 x 10% = ~120. Expected revenue = 120 x BRL 137.51 x 2.11 = ~BRL 34,800. Net profit = ~BRL 16,770. This is Slide 8. | Selina | Single costed recommendation slide | Done
Priority 2 — Fix CLV Formula
Replace flat 3% with model P(repeat) | Current CLV assigns P(repeat) = 3% to all one-time buyers. Replace with each customer's actual predicted P(repeat) from the classifier. This creates a more granular CLV distribution and identifies High-Potential Dormant Buyers — one-time buyers with above-average predicted repeat probability. This is your primary targeting audience. | Selina | Updated CLV distribution + High-Potential Dormant Buyers segment | Done
Priority 3 — Validation Slide
Design randomized experiment | Prof flagged the causal gap: does voucher use cause repeat purchase, or are voucher users just different buyers? Propose: randomly assign first-time buyers to receive or not receive a post-purchase voucher. Measure repeat rate at 90 days. Calculate incremental profit per voucher sent. No new analysis needed — just clear thinking. This is Slide 9. | Hanna | Experiment design slide | Done
Priority 4 — Naming & Framing
Replace 'the platform' with Olist | Prof has flagged this twice. Replace every instance of 'the platform' with 'Olist' throughout the document and all presentation slides. Also name the client explicitly on Slide 1. | Shrikar | Updated doc + Slide 1 | To do
Name the target segment | Explicitly name the primary targeting audience: 'High-Potential Dormant Buyers' — one-time buyers with above-average P(repeat) who haven't returned yet. Use this label consistently across all slides. |  | Named segment used throughout deck | To do
Geographic & Category Mapping — deprioritized, complete only if time allows after Priorities 1-4
Regional CLV mapping | Join high-CLV customers to geo table. Map by state/city. Only include if it directly supports the targeting P&L recommendation. | Member 4 | Regional CLV heatmap | If time allows
Category concentration | Identify categories associated with high-CLV buyers. Only include if it adds to the recommendation, not as a standalone finding. | Member 4 | Category CLV breakdown | If time allows
Segmentation Matrix & Final Narrative
Segmentation matrix | Compile CLV tiers, P(repeat) bands, and key experience drivers into a decision framework. Minimum columns: segment name, estimated CLV, key driver, recommended intervention, cost, expected net profit. High-Potential Dormant Buyers = primary segment. | Augus | Complete decision framework | Done- currently has placeholder names and strategies
Final business narrative | Story arc: Olist has 3% repeat rate → CLV gap is 60x → model identifies 1,202 high-potential customers → targeting with BRL 15 voucher generates BRL 16,770 net profit → here is how to validate causality before scaling. One clear recommendation, one price tag. | Manvi | Presentation narrative | To do
Visualization |  | All
Integration & Presentation — all members
Cross-check all numbers | Ensure targeting P&L, CLV, and feature importance all reference consistent definitions and customer counts. | All 5 | Consistent final output | To do
Final presentation | 7-minute pitch. One specific recommendation with a price tag, a targeting rule, and a net profit estimate. Name Olist on Slide 1. | All 5 (Member 5 lead) | Submitted presentation | To do